## Event_Calculator
Event Timeline Calculator
Activities | Calculator | Date enter event date below | Day | Details
Event Date |  | 2012-12-12 | Wednesday | Hold your fundraising activity. Provide a schedule of event day activities and event information. Depending on your fundraiser, this day may require the majority of your volunteer help. You've worked hard for this day so be sure to have fun!
Make final preparations for your fundraising activity |  | 2012-12-11 | Tuesday | For outdoor fundraising events, confirm food & beverage deliveries, mark routes with spray chalk and arrange distribution of t-shirts (if applicable). For a bike ride make arrangements for bicycle drop off and labeling the night before and the morning of your event.
Last Date for Collecting and Totaling Donations | 2 | 2012-12-10 | Monday | Last day for donations - Volunteers to count money. Total all donations, assign prize tiers and identify top earners for top prize drawings at awards ceremony.
Week Three Collection Date | 2 | 2012-12-07 | Friday | Schools offer prizes to top earners and classrooms - Volunteers to count money turned in every Friday, mark envelopes and return to participants. Organize event-day food and drink donations, schedule pick-up.
Week Two Collection Date | 2 | 2012-11-30 | Friday | Schools to offer prizes to top earners and classrooms- Volunteers to count money turned in every Friday, mark envelopes and return to participants.
Week One Collection Date | 2 | 2012-11-23 | Friday | Schools may offer prizes to top earners and classrooms - Volunteers to count money turned in every Friday, mark envelopes and return to participants.
Kick Off Date | 2 | 2012-11-16 | Friday | Hold kickoff to announce fundraiser to school students. Display donated prizes. Total all corporate donations - Schools: Download donation code information and print labels and student information on envelopes. Stuff envelopes with take-home information for parents. Email donation codes to participants and parents through the campaign management interface.
Order T-shirts |  | 2012-11-16 | Friday | If you Enabled Online Registration, you should have selected the "Registration Cutoff Date" to be the same day as the kickoff. Shirts will ship within 10 business days of ordering and receipt of approved artwork.
Create donations codes and update your FundMonkey web page with business sponsors. |  | 2012-11-12 | Monday | Update your FundMonkey web page by adding business sponsors with web links to their web pages. Create participant pledge codes by adding users to Campaign Management system.
Make final collections of cash and in-kind donations from business sponsors |  | 2012-11-12 | Monday | Have all prizes ready and on display for school kickoff. Purchase additional prizes for kickoff if needed.
Order event items |  | 2012-11-06 | Tuesday | Order Tyvek numbered racing bibs, chalk-based road paint and other event support items you will need for the day of your event from the FundMonkey shop.
Order marketing materials |  | 2012-11-01 | Thursday | Last chance to order envelopes and other materials from your Campaign Consultants.
Final follow up on mailings |  | 2012-10-15 | Monday | Follow up with local businesses by phone and in person. Seek food and drink for the day for your event.
Follow up on second mailing |  | 2012-10-08 | Monday | Follow up by phone with second mailing. If you haven't done so already, recruit volunteers.
Mailing follow up and second mailing |  | 2012-10-01 | Monday | Make follow up phone calls to potential business sponsors - Send second mailing to local businesses and merchants.
Determine the route for your fundraising event |  | 2012-09-27 | Thursday | Determine your event route and the number of volunteers needed for supporting your event.
Mail sponsorship requests to local businesses and merchants |  | 2012-09-24 | Monday | Print and send mailings to local business seeking donations or in-kind contributions of food, drink or goodie bag stuffers.
Choose Registration Options and plan a registration drive |  | 2012-09-12 | Wednesday | Enabling online registration is optional. Options can include up to 2 Events, Teams, Team Leaders, online t-shirt ordering and optional fees associated with each of the two events. Select a Registration Cutoff date the same as your kickoff date. Hold a registration drive at back to school nights or open houses. Get the participation of classroom teachers. Send home fliers to encourage school students to register online in order to qualify for prizes and contests.
Create FundMonkey web page |  | 2012-09-12 | Wednesday | Login to your account with the User ID and password sent to your email address. Change your password. Reserve your unique sub domain and create your FundMonkey web page as early as possible with our easy-to-use templates.
Let's get Started - Register for a FundMonkey License |  | 2012-09-10 | Monday | Get permissions from city and school officials for your projected date. Register on-line with a credit card download our registration form and send with payment.
Every FundMonkey fundraiser is different. This timeline is simply a rough guide to chart your progress and to help you be aware of a few of the details that will need your attention. This timeline is roughly based on a 90 day schedule. For a shorter schedule you may condense many of the line items in the grey to 30 days or less leading up to the kickoff and shorten you campaign by one week. We've had groups use our service with only two weeks from registration to fundraiser with successful results.
Formulas:
Date enter event date below = [Date enter event date below, row above]-1
Date enter event date below = (D5-4)+[Calculator]
© 2010 Empowerment Solutions, LLC
All Rights Reserved